## Team Building Retrea
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=team-building-retreat
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Initial Planning
Project Kick-off
Team Assessment
Goals Definition
Timescale Establishment
Resource Identification
Stakeholder Identification
Project Scope Definition
Risk Assessment
Strategy Formulation
Planning Review
Approval Seek
Plan Finalization
Team Consultation
Team Survey Preparation
Survey Distribution
Response Collection
Data Analysis
Team Meeting Scheduling
Meeting Preparation
Individual Consultations
Group Discussions
Feedback Collection
Consultation Summary
Action Plan Development
Team Feedback Review
Venue Selection
Venue Criteria Definition
Potential Venue Research
Long-list Creation
Preliminary Contact
Initial Venue Evaluation
Short-list Creation
Detailed Venue Inspection
Venue Comparison
Cost Negotiation
Venue Selection
Contract Review
Venue Booking Confirmation
Activity Planning
Activity Objectives Definition
Brainstorming Session
Preliminary Activity List
Activity Research
Cost Estimation for Each Activity
Time Allocation for Each Activity
Activity Approvals
Detailed Activity Development
Activity Schedule Creation
Resources Allocation for Activities
Activity Brief Preparation
Final Activity Plan Review
Budget Allocation
Budget Requirement Estimation
Initial Budget Drafting
Income Source Identification
Expense Classification
Cost Analysis
Funding Allocation
Budget Reviewal
Budget Adjustment
Final Budget Approval
Budget Distribution
Budget Tracking System Setup
Budget Contingency Plan Creation
Final Agenda Creation
Preliminary Agenda Drafting
Time Slot Allocation
Breaks and Meals Scheduling
Speaker or Facilitator Scheduling
Activity Placement
Agenda Review Session
Suggested Changes Incorporation
Final Agenda Drafting
Agenda Proofreading
Agenda Approval
Agenda Printing
Agenda Distribution
Logistics Coordination
Transport Arrangements
Accommodation Booking
Meal Planning
Equipment Procurement
Venue Setup Coordination
Staffing Allocation
Emergency Procedures Planning
Documentation Preparation
Communication Plan Creation
Timeline Confirmation
Final Logistics Checklist
Last-minute Adjustments Handling
Pre-Retreat Briefing
Briefing Agenda Preparation
Briefing Materials Compilation
Team Notification
Venue Preparation
Briefing Presentation Creation
Pre-Briefing Review
Briefing Delivery
Question & Answer Session
Discussion of Expectations
Feedback Collection
Post-Briefing Evaluation
Final Retreat Instructions Issuance
Retreat Execution
Retreat Kick-off
Participant Registration
Welcome Speech Delivery
Activity Initiation
Ongoing Facilitation
Meal and Break Management
Problem Troubleshooting
Participant Engagement Monitoring
Daily Wrap-up
Evening Activities Coordination
Final Day Execution
Closing Ceremony Management
Post-Retreat Evaluation
Feedback Form Distribution
Feedback Collection
Data Compilation
Feedback Analysis
Evaluation Report Drafting
Lessons Learned Identification
Improvement Suggestions Listing
Report Review Session
Adjustments and Finalization
Report Approval
Evaluation Report Distribution
Follow-up Action Plan Development