## TV Commercial Productio
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=tv-commercial-production
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Project Initiation
Project Kick-off
Stakeholder Identification
Project Goals Definition
Project Budget Planning
Resource Identification
Project Timeline Development
Risk Assessment
Project Charter Creation
Project Team Formation
Communication Plan Development
Project Management Tools Setup
Project Initiative Approval
Concept Development
Market Research
Competitor Analysis
Target Audience Identification
Brainstorming Sessions
Conceptualization Meetings
Creative Theme Development
Storyboard Sketching
Concept Validation
Client Feedback Collection
Concept Revisions
Final Concept Approval
Documentation of Concept Development
Script Writing
Outline Creation
Character Development
Scene Description
Dialogue Writing
Script Formatting
Script Review
Feedback Incorporation
Script Revisions
Table Read
Final Draft Creation
Legal Review
Script Approval
Pre-production Planning
Location Scouting
Production Schedule Development
Equipment Reservation
Crew Assignment
Shot List Creation
Storyboard Finalization
Casting Finalization
Costume Design and Planning
Set Design and Planning
Legal Permissions and Contracts
Logistics Planning
Pre-Production Meeting and Finalization
Casting
Role Definition
Casting Call Announcement
Application Collection
Pre-Screening of Applications
Initial Auditions
Callbacks
Screen Tests
Final Selections
Actor Notification
Contract Negotiations
Cast Orientation
Rehearsal Scheduling
Filming
Set Construction
Equipment Setup
Lighting Arrangement
Rehearsal
Costume and Makeup Application
Scene Filming
Sound Recording
Shot Retakes
Daily Dailies Review
Scene Wrap-up
Equipment Dismantling
Set Breakdown
Post-production Editing
Footage Logging
Rough Cut Creation
Scene Sequencing
Color Grading
Sound Editing
Visual Effects Addition
Music Incorporation
Title and Credits Addition
Final Cut Creation
Client Review
Editing Revisions
Final Edit Approval
Special Effects Integration
Visual Effects Planning
Storyboard Revisiting
Computer-Generated Imagery (CGI) Designing
Special Effects Animation
SFX Scene Integration
Lighting Adjustments
Special Effects Rendering
VFX and Film Syncing
Quality Check
Feedback Incorporation
Special Effects Revisions
Final Effects Approval
Sound Designing
Sound Design Planning
Dialogue Editing
Sound Effects Recording
Background Noise Selection
Music Composition or Selection
Soundtrack Syncing
Sound Mixing
Volume Leveling
Sound Quality Check
Client Feedback Collection
Sound Design Revisions
Final Sound Design Approval
Final Review and Distribution
Complete Project Review
Quality Assurance Testing
Client Final Review
Final Edits and Adjustments
Approval for Distribution
Press Kit Creation
Media Release Scheduling
Distribution Channel Selection
Format Conversions
Distribution Execution
Marketing and Promotion
Feedback and Evaluation Collection