## TV Commercial Serie
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=tv-commercial-series
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Concept Development
Market Research
Audience Targeting
Product Analysis
Brand Ideation
Scenario Brainstorming
Goal Setting
Concept Drafting
Creative Workshop
Concept Refinement
Storyboard Creation
Concept Presentation
Feedback Incorporation
Script Writing
Theme Identification
Plot Development
Character Creation
Dialogue Construction
Scene Sequencing
Script Drafting
Review & Revision
Table Read
Feedback Gathering
Script Refinement
Final Script Approval
Distribution of Scripts
Pre-production Planning
Budget Estimation
Project Timeline Creation
Equipment Procurement
Personnel Hiring
Location Finalisation
Production Schedule Design
Rehearsal Planning
Set Designing
Costume Sourcing
Legal Clearance Obtaining
Risk Assessment
Contingency Planning
Casting
Role Definition
Casting Call Announcement
Application Collection
Talent Screening
First Round Auditions
Callbacks
Final Auditions
Role Offering
Talent Confirmation
Contract Signing
Schedule Coordination
Casting Announcement
Location Scouting
Location Requirement Identification
Initial Research
Potential Site Listing
Site Visits
Site Photography
Light Testing
Acoustic Testing
Accessibility Evaluation
Risk Assessment
Location Shortlisting
Permission Negotiating
Final Location Selection
Filming
Pre-shoot Briefing
Set-up of Equipment
Makeup & Wardrobe Preparation
Scene Rehearsals
Camera Positioning
Lighting Setup
Sound Check
Principal Photography
B-roll Filming
Scene Wrap-up
Daily Review
Equipment Pack-up
Post-production Editing
Footage Backup
Rough Cut Creation
Video Editing
Sound Editing
Color Correction
Visual Effects Addition
Audio Mixing
Voiceover Integration
Subtitle Addition
Final Cut Review
Changes Implementation
Final Edit Approval
Special Effects & Sound Design
Effects Planning
Soundtrack Selection
Foley Sound Recording
Digital Effects Design
Practical Effects Testing
Sound Effects Integration
Visual Effects Application
Sound Mixing
Effects Review
Sound Mastering
Adjustments Based on Feedback
Final Effects & Sound Approval
Review & Approval
Internal Screening
Feedback Collection
Changes Identification
Edit Amendments
Quality Assurance Check
Legal Compliance Verification
Client Review
Client Feedback Incorporation
Final Review
Sign-off from Key Stakeholders
Approval Documentation
Archive & Backup
Broadcast Launch
Broadcast Date Scheduling
Promotional Material Creation
Media Plan Development
Press Release Writing
Social Media Teasing
Press Conference Hosting
Commercial Distribution
Broadcast Timing Coordination
Live Broadcast Monitoring
Audience Engagement Tracking
Feedback Analysis
Performance Reporting