## urban-plaza-desig
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=urban-plaza-design
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Initial Research
Project Brief understanding
Preliminary Site Visit
Historical Context Study
Social Demographics Study
Current Use Assessment
Environmental Impact Analysis
Local Regulation Review
Market Trend Analysis
Identification of Potential Challenges
Comparative Study of Similar Projects
Preliminary Budget Estimation
Define Project Timeline
Site Analysis
Physical Site Inspection
Topography Analysis
Soil Investigation
Landscape Assessment
Accessibility Evaluation
Infrastructure Assessment
Climate and Sun Path Analysis
Noise and Air Quality Study
View Analysis
Surveys of Existing Structures
Mapping of Site Features
Preliminary Site Report Compilation
Conceptual Design
Brainstorming Sessions
Sketching Initial Ideas
Developing Design Concepts
Reviewing Design Guidelines
Creating Preliminary Models
Analyzing Space Usage
Establishing Material Palette
Evaluation of Sustainability Options
Assessing Feasibility of Concepts
Cost and Budget Considerations
Refinement of Selected Concept
Preparation of Conceptual Design Presentation
Stakeholder Consultation
Identification of Stakeholders
Planning Stakeholder Meetings
Preparing Presentation Material
Conducting Initial Meetings
Gathering Stakeholder Feedback
Documenting Meeting Minutes
Assessing Feedback
Modifying Design Based on Feedback
Preparing Response to Feedback
Conducting Follow-up Meetings
Finalizing Design Changes
Obtaining Stakeholder Approval
Detailed Design Planning
Creation of Detailed Design Brief
Defining Functional Areas
Establishing Design Specifications
Developing Detailed Drawings
Conducting Material Selection
Lighting and Acoustic Planning
Landscaping Detailed Design
Integration of Infrastructure
Safety and Accessibility Considerations
Detailed Cost Estimation
Design Review and Amendments
Final Detailed Design Approval
Design Approval
Preparing Design Presentation
Scheduling Approval Meetings
Presenting Design to Stakeholders
Addressing Queries and Concerns
Collecting Feedback on Design
Documenting Meeting Outcomes
Incorporating Feedback into Design
Revising Cost and Time Estimates
Preparing Final Design Documents
Submitting Design for Approval
Tracking Approval Process
Receiving Design Approval Confirmation
Procurement Process
Identifying Required Resources
Developing Procurement Strategy
Preparing Request for Proposal
Inviting Bids from Vendors
Evaluating Vendor Proposals
Conducting Vendor Selection
Negotiating Contract Terms
Finalizing Vendor Contracts
Issuing Purchase Orders
Managing Delivery Schedules
Quality Checking of Received Resources
Documenting Procurement Process
Construction Phase
Organizing Kick-off Meeting
Assigning Roles and Responsibilities
Setting Up Site Facilities
Beginning Foundation Work
Constructing Main Structure
Installing Infrastructure Systems
Carrying Out Interior Work
Implementing Landscape Design
Conducting Regular Site Inspections
Managing Construction Schedule
Addressing On-Site Issues
Completing Final Construction Tasks
Quality Assurance Check
Developing Quality Checklists
Conducting Initial Walkthrough
Checking Structural Integrity
Verifying Infrastructure Systems
Inspecting Interior Work
Assessing Landscape Implementation
Confirming Compliance with Design
Evaluating Material Quality
Identifying Rectification Requirements
Conducting Re-inspections Post Corrections
Documenting Quality Assurance Results
Finalizing Quality Assurance Report
Project Handover and Closure
Preparing Handover Documents
Compiling Project Reports
Organizing Final Project Meeting
Confirming Completion of Tasks
Handing Over the Project to Client
Providing Necessary Training to Users
Finalizing Outstanding Payments
Releasing Retained Resources
Gathering Project Feedback
Conducting Project Review
Documenting Lessons Learned
Formally Closing the Project