## User Interface Desig
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=user-interface-design
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Requirements Gathering
Project Kick-off
Stakeholder Identification
Define Project Scope
Identify User Needs
Analyze Competitive Products
Establish Technical Constraints
Define Functional Specifications
Document Performance Requirements
Identify Safety and Security Requirements
Determine Design Constraints
Review and Approval of Requirements
Requirements Documentation.
User Research
Identifying Target Users
Defining User Personas
Conducting Surveys
Executing User Interviews
Field Studies
Ethnographic Research
Observing User Behavior
Conducting Focus Groups
Analyzing User Feedback
User Journey Mapping
Synthesizing Research Data
Documenting Research Findings
Information Architecture
Define Information Goals
Content Inventory
Content Grouping
Design Site Structure
Develop Navigational Scheme
Create User Flow Diagrams
Define Metadata and Taxonomy
Design Search Systems
Develop Wireframes for Key Pages
Information Architecture Testing
Revise Based on User Feedback
Finalize Information Architecture Design
Wireframing
Define User Interface (UI) Requirements
Sketch Initial Ideas
Create Low-Fidelity Wireframes
Validate Wireframes Internally
Conduct Wireframe Usability Testing
Refine Wireframes Based on Feedback
Create High-Fidelity Wireframes
Check Wireframes Against User Flows
Review Wireframes with Stakeholders
Iterate Wireframes Based on Reviews
Prepare Wireframe Documentation
Handover Wireframes for Prototyping
Prototyping
Define Prototype Scope
Choose Prototyping Tool
Create Interactive Elements
Link Screens Together
Develop Basic Navigation
Add Content to Prototype
Internal Testing of Prototype
Iterate Based on Internal Feedback
User Testing of Prototype
Gather and Analyze User Feedback
Refine Prototype Based on User Feedback
Finalize and Document Prototype
Visual Design
Define Visual Design Goals
Research Design Trends
Choose Color Scheme
Select Typography
Design UI Elements
Create Iconography
Layout Screen Designs
Add Imagery and Graphics
Apply Branding Elements
Review and Revise Design
Test Visual Design Usability
Finalize and Document Visual Design
Usability Testing
Define Testing Objectives
Select User Testing Methods
Recruit Test Participants
Develop Test Scenarios
Prepare Test Environment
Conduct Usability Tests
Record User Interactions
Collect User Feedback
Analyze Test Results
Identify Usability Issues
Recommend Design Improvements
Document Testing Process and Findings
User Feedback
Define Feedback Goals
Select Feedback Channels
Develop Feedback Questions
Invite Users for Feedback
Collect User Feedback
Record Feedback Responses
Organize Feedback Data
Analyze Feedback Results
Identify Common Themes
Prioritize Feedback Suggestions
Formulate Design Revisions
Document Feedback Process and Insights
Design Iteration
Review Feedback and Test Results
Identify Areas for Improvement
Prioritize Design Changes
Sketch Solutions for Identified Issues
Revise Wireframes
Adjust Prototype
Modify Visual Design
Conduct Internal Review
Retest Adjusted Design
Refine Design Based on Retesting
Finalize Iterative Design Changes
Document Iteration Process and Changes
Implementation and Launch
Prepare Design Handoff
Coordinate with Development Team
Implement Design into Code
Perform Quality Assurance Tests
Debugging and Issue Resolution
Review Final Product
Prepare Launch Plan
Load Testing and Stress Testing
Final User Acceptance Testing
Final Design and Functionality Check
Official Product Launch
Post-Launch Monitoring and Maintenance