## website-navigation-optimizatio
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=website-navigation-optimization
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Requirements Analysis
Stakeholder Identification
Initial Project Meeting
Project Scope Definition
User Needs Identification
Technical Constraints Analysis
Competitor Website Analysis
Functionality Requirements Gathering
Content Requirements Gathering
User Interface Requirements Gathering
Accessibility Requirements Gathering
Requirements Documentation
Requirements Review and Approval
Website Audit
Website Inventory Compilation
Website Structure Analysis
Page Load Speed Evaluation
Desktop Compatibility Testing
Mobile Compatibility Testing
SEO Performance Review
Content Quality Assessment
User Experience Examination
Security Review
Social Media Integration Analysis
Website Audit Report Development
Audit Findings Presentation
User Behavior Study
Target Audience Identification
User Behavior Research Plan Development
Data Collection Method Selection
User Surveys Design
User Interviews Preparation
User Testing Sessions Arrangement
User Surveys Conducting
User Interviews Executing
User Testing Data Collection
User Behavior Data Analysis
User Behavior Report Creation
User Behavior Study Findings Presentation
Information Architecture Design
Information Architecture Goals Definition
Existing Information Architecture Evaluation
User Flow Mapping
Site Structure Drafting
Navigation Scheme Creation
Labeling System Development
Search System Design
Metadata Structure Planning
User Scenarios Testing
Information Architecture Refinement
Information Architecture Documentation
Stakeholder Review and Approval
Navigation Interface Prototyping
Navigation Interface Design Brief Creation
Wireframing Initial Sketches
Navigation Elements Positioning
Color and Typography Selection
Interactive Elements Design
Low-fidelity Prototype Development
Usability Testing of Low-fidelity Prototype
Feedback Incorporation
High-fidelity Prototype Development
Usability Testing of High-fidelity Prototype
Final Modifications and Refinements
Prototype Approval and Sign-off
User Testing and Feedback
User Testing Plan Development
Participant Recruitment
Test Environment Set-Up
Test Scenario Creation
User Test Sessions Scheduling
User Test Conducting
User Feedback Collection
User Test Observations Recording
Data Analysis and Interpretation
User Feedback Review
Changes Prioritization
User Testing Report Preparation
Navigation System Implementation
Implementation Plan Development
Required Technologies Selection
Development Environment Setup
Navigation System Coding
Integration of Navigation System with Website
Basic Functionality Testing
Debugging and Issue Resolution
Cross-browser Compatibility Testing
Mobile Responsiveness Testing
Navigation System Optimization
Final Implementation Review
Navigation System Launch
Website Integration
Integration Strategy Development
Backup of Existing Website
Integration Requirements Finalization
Existing Website Components Review
Creation of Integration Scripts
Integration of Navigation System with Website Components
Compatibility Testing
Performance Testing
Integration Issue Resolution
Integration Approval and Confirmation
Live Website Updating
Post-integration Testing
Quality Assurance Testing
Test Plan Creation
Test Cases Development
Functional Testing
Usability Testing
Performance Testing
Security Testing
Cross-Browser Testing
Mobile Responsiveness Testing
Bug Reporting
Bug Fixing and Retesting
Final Test Cycle
Test Summary Report Preparation
Project Closure and Evaluation
Final Project Review
Stakeholder Feedback Collection
Performance Metrics Analysis
Success Criteria Evaluation
Project Documentation Finalization
Lessons Learned Documentation
Project Deliverables Sign-off
Release of Project Resources
Project Closure Report Preparation
Project Closure Meeting
Project Archive Creation
Post-Project Review Schedule