## Wedding da
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=wedding-day
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Engagement Announcement
Engagement Ring Selection
Proposal Planning
Proposal Execution
Family Notification
Close Friends Notification
Official Engagement Announcement
Social Media Announcement
Engagement Party Planning
Engagement Party Invitation Creation
Engagement Party Guest List Finalization
Engagement Party Execution
Post-Announcement Reflection
Budget Planning
Financial Review
Budget Allocation Outline
Venue Budgeting
Catering Budgeting
Dress and Suit Budgeting
Decor and Flowers Budgeting
Entertainment Budgeting
Invitations and Stationery Budgeting
Transportation Budgeting
Honeymoon Budgeting
Emergency Fund Setup
Budget Finalization and Approval
Venue Selection
Venue Research
Shortlist Creation
Budget Compatibility Check
Site Visit Scheduling
Site Visit Execution
Venue Capacity Evaluation
Venue Location Assessment
Venue Terms and Conditions Review
Venue Availability Confirmation
Price Negotiation
Venue Booking
Venue Confirmation Receipt
Guest List Compilation
Initial Guest Brainstorming
Family Member Listing
Friend Listing
Colleague Listing
Special Guest Consideration
Capacity Constraint Review
Preliminary List Review
Guest List Pruning
Final List Approval
Contact Information Gathering
Guest List Formatting
Guest List Finalization
Invitations Dispatch
Invitation Design Selection
Invitation Wording Finalization
Invitation Printing
Guest Address Compilation
Envelope Addressing
Invitation Packaging
Postage Calculation
Postage Purchasing
Invitations Mailing
Digital Invitations Sending
RSVP Tracking Setup
Confirmation Receipt Verification
Dress and Suit Fitting
Style Research
Appointment Booking
Initial Fitting Session
Dress/Suit Selection
Measurement Taking
First Alteration
Second Fitting Session
Second Alteration
Final Fitting Session
Dress/Suit Collection
Accessory Trial
Final Dress/Suit Approval
Menu and Decor Finalization
Event Theme Determination
Decor Style Selection
Menu Brainstorming
Caterer Consultation
Food Tasting
Menu Selection
Dietary Requirements Addressing
Decor Vendor Meeting
Decor Selection
Table Layout Finalization
Menu and Decor Review
Final Approval and Payment
Rehearsal Dinner
Rehearsal Date Setting
Guest List Compilation
Venue Booking
Menu Planning
Decor Deciding
Rehearsal Invitations Sending
Rehearsal Run-Through Planning
Rehearsal Dinner Execution
Speeches and Toasts
Rehearsal Clean-Up
Last Minute Adjustments
Pre-Wedding Rest
Ceremony Execution
Venue Preparation
Vendor Coordination
Bridal Party Arrival
Guest Seating
Ceremony Start
Vows Exchange
Ring Exchange
Pronouncement of Marriage
First Kiss as Married Couple
Recessional
Post-Ceremony Photos
Reception Transition
Post-Wedding Wrap-up
Venue Clean-Up
Vendor Payments Finalization
Gift Collection
Thank You Notes Preparation
Wedding Dress Preservation
Marriage Certificate Collection
Name Change Documentation
Wedding Photo Collection
Honeymoon Packing
Honeymoon Departure
Post-Wedding Reflection
Budget Review and Closure