## wireless-network-expansio
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=wireless-network-expansion
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Project Initiation
Project Briefing
Team Formation
Project Scope Definition
Identifying Stakeholders
Setting Objectives
Establishing Timelines
Defining Budget
Risk Assessment
Project Approval
Developing Project Charter
Communication Plan
Kick-off Meeting
Wireless Needs Assessment
User Requirement Gathering
Coverage Area Analysis
Traffic Estimation
Existing Network Evaluation
Wireless Technology Selection
Security Needs Identification
Capacity Planning
Redundancy Planning
Budget Constraints Analysis
Wireless Standards Compliance
Needs Assessment Report
Stakeholder Presentation
Network Design Planning
Defining Network Topology
Selecting Network Devices
Access Point Placement Planning
Network Security Design
Integration Planning
Scalability and Flexibility Analysis
Bandwidth Allocation Planning
IP Addressing Scheme Design
Creating Network Diagrams
Network Disaster Recovery Planning
Design Documentation
Design Approval Process
Procurement of Equipment
Equipment Needs Identification
Vendor Research
Request for Quotation (RFQ)
Bid Analysis
Vendor Selection
Purchase Order Issuance
Contract Negotiation
Purchase Approval
Order Placement
Equipment Delivery Schedule
Equipment Receipt Verification
Equipment Inventory Management
Site Preparation
Site Survey
Space Allocation
Infrastructure Assessment
Power Supply Arrangement
Cooling System Setup
Security Measures Implementation
Equipment Installation Area Preparation
Cable Routing Plan
Site Safety Procedures
Equipment Unpacking and Inspection
Disposal of Packaging
Site Clean-up and Ready Confirmation
Network Installation
Installation Team Briefing
Equipment Setup
Cable Installation
Access Point Installation
Network Device Configuration
Security Features Setup
Network Connection Verification
Physical Network Layout Verification
System Integration
Backup and Recovery Setup
Installation Documentation
Installation Completion Sign-off
Network Configuration
Configuration Plan Review
IP Address Assignment
Network Devices Configuration
Wireless Access Points Setup
User Access Control Configuration
Network Security Features Activation
Bandwidth Management Configuration
Load Balancing Setup
Network Monitoring Tool Configuration
Backup and Recovery Configuration
Configuration Testing and Verification
Configuration Documentation
Network Testing
Test Plan Development
Connectivity Testing
Speed and Performance Testing
Network Security Audit
Load Balancing Testing
Redundancy Testing
Bandwidth Utilization Review
User Access Testing
Network Monitoring Tool Testing
Backup and Recovery Testing
Issue Identification and Resolution
Test Report Preparation
Project Handover
Project Completion Review
Final Report Preparation
User Manuals Preparation
Network Training Planning
Stakeholder Communication
User Training Sessions
Handover Documentation Compilation
Project Closure Meeting
Handover of Network Control
Post-handover Support Planning
Final Payment Processing
Project Sign-off and Closure
Post-Implementation Review
Post-Implementation Review Planning
Stakeholder Interviews
Network Performance Analysis
User Feedback Collection
Security Audit Review
Financial Review
Lessons Learned Documentation
Recommendation for Improvements
Review Report Compilation
Presentation to Stakeholders
Implementation of Improvement Actions
Post-Implementation Review Closure